## Sheet1
Risk | Risk statement | Response strategy | objectives | likelihood | impact | risk level
burglary | if a burglary was to occur equipment such as laptops and PCs could be stolen which means that there will be no device to complete work on therefore development time will be drastically lost as new equipment will have to be sought after | make sure the house has an alarm which is set every time you leave the house also ensure that you have good locks on your doors which would make it hard for burglars to gain entry into your home also having a lock for the room where the laptop and other devices are kept for extra safety measure. | to prevent burglary and loss of equipment such as laptops and PCs which I used for developing. | Likely |  | 1
spilt liquid's | liquid's the near the workspace such as water coffees and tea could accidentally spill and get all over equipment damaging pieces and laptops therefore work will no longer be able to continue | ensure the all liquid's are kept well away from equipment such as PCs and laptops. | to ensure the liquid's do not spill onto equipment causing damage to PCs and laptops | likely |  | 2 |  |  | Impact
accidental deletion | if part or all of a project is deleted you would have to recreate the part the has been deleted which will take time. | use resources such as GitHub as work stored on GitHub can be saved securely and won't be lost full | ensure work is saved I'm backed up to prevent losing work | Unlikely |  | 3 |  |  | Minimal | Moderate | Significant
illness | developers could fall ill which would mean they are unable to complete work which means development time who will be lost. | keep good hygiene ensure working environment is clean and safe and take care of overall health. | is sure that you are healthy and fit to work so the development is not lost. | unlikely |  | 4 | Liklihood | Likely | 1 | 4 | 7
GitHub hacked | GitHub account can be hacked and work can be lost | don't allow anyone to know your account credentials and always have a long secure password | to prevent GitHub account from being hacked | unlikely |  | 5 |  | Unlikely | 2 | 5 | 8
Internet outage | this will affect the development of a project as the Internet will not be able to be used for things such as research and development also it will affect backing up work on resources such as GitHub as there will be no Internet access | make sure that all work is saved on more than one device and onto usb's as well as GitHub to ensure that work is saved and just try to always make sure that you have a stable working reliable Internet connexion and have mobile data at hand if Internet connexion is ever lost | to ensure productivity of a project and make sure work is saved onto social such as GitHub. | Possible |  | 6 |  | Highly unlikely | 3 | 6 | 9
power outage | a power outage could mean a lot of development time as PC would lose power if there was a power outage | have a laptop which is fully charged and in the case of a power outage find a location where you could go and carry on work | to try and lose at least development time as possible in the event of a power outage | unlikely |  | 7
GitHub taken down | if all work is stored on GitHub and GitHub is taken down all work will be lost and would have to be re done which will take significant amount time | have work saved on other sources besides GitHub and have backups on other pieces and things such as usb's | to keep work secure and have copies | highly unlikely |  | 8

## Sheet2
Impact
|  | Moderate | Significant | Severe
Liklihood | Likely | 1 | 4 | 7
| Unlikely | 2 | 5 | 8
| Highly unlikely | 3 | 6 | 9